## Test Plan
Document Control
Document Information | Details
Project Name | Hotel Booking API Testing
URL | https://automationintesting.online/
Prepared By | Minh Nguyet
Date | 2025-06-10
Status
Introduction
This document describes the test plan for the Hotel Booking API testing project. It defines the testing objectives, scope, approach, environment, resources, deliverables, risks, and acceptance criteria for validating the functionality and performance of the API.
Test Scope
1.In Scope
API ID | Endpoint | Method | Description
API-001 | /auth | POST | Create authentication token
API-002 | /booking | GET | Retrieve booking IDs
API-003 | /booking/:id | GET | Retrieve a specific booking
API-004 | /booking | POST | Create a new booking
Testing Type | Purpose | Tool
1.Functional Testing 2.Authentication Testing 3.Negative Testing | Verify API functionality Verify authentication behavior Verify invalid requests and error handling | Postman Postman Postman
2.Out of scope
1.UI testing 2.Mobile application testing 3.Database testing 4.Performance testing of the database 5.Security penetration testing 6.Infrastructure testing 7.Manual security assessment 8.PUT and DELETE booking operations until their API specifications are available
Test Data
Authentication Test Data
Username: admin Password: password123
Booking Test Data
{ "firstname": "Jim", "lastname": "Brown", "totalprice": 111, "depositpaid": true, "bookingdates": { "checkin": "2018-01-01", "checkout": "2019-01-01" }, "additionalneeds": "Breakfast" }
Entry Criteria
API documentation is available. API endpoints are accessible. Test environment is available. Required test data is available. Postman is installed and configured. Apache JMeter is installed and configured. Test scenarios and test cases have been reviewed.
Exit Criteria
All planned test cases have been executed. Functional API testing has been completed. Negative testing has been completed. Authentication testing has been completed. Load testing has been completed. Stress testing has been completed. Identified defects have been documented. Test results have been reviewed. Final Test Summary Report has been prepared.

## Test Scenario
API AUTH 001/ POST
Scenario ID | API ID | Module | Test Scenario | Test Type | Priority
TS-AUTH-001 | API-001 | Authentication | Verify authentication with valid credentials | Positive | High
TS-AUTH-002 | API-001 | Authentication | Verify authentication with invalid username | Negative | High
TS-AUTH-003 | API-001 | Authentication | Verify authentication with invalid password | Negative | High
TS-AUTH-004 | API-001 | Authentication | Verify authentication with missing username | Negative | High
TS-AUTH-005 | API-001 | Authentication | Verify authentication with missing password | Negative | High
TS-AUTH-006 | API-001 | Authentication | Verify authentication response contains a valid token | Functional | High
API-002 — GET/ booking
Scenario ID | API ID | Module | Test Scenario | Test Type | Priority
TS-BOOK-001 | API-002 | Booking List | Verify retrieving all booking IDs | Positive | High
TS-BOOK-002 | API-002 | Booking List | Verify retrieving booking IDs by firstname | Functional | Medium
TS-BOOK-003 | API-002 | Booking List | Verify retrieving booking IDs by lastname | Functional | Medium
TS-BOOK-004 | API-002 | Booking List | Verify retrieving booking IDs by check-in date | Functional | Medium
TS-BOOK-005 | API-002 | Booking List | Verify retrieving booking IDs by check-out date | Functional | Medium
TS-BOOK-006 | API-002 | Booking List | Verify retrieving booking IDs using multiple filters | Functional | Medium
TS-BOOK-007 | API-002 | Booking List | Verify API behavior with invalid filter values | Negative | Medium
TS-BOOK-008 | API-002 | Booking List | Verify booking list response structure | Functional | High
API-003 — GET/ booking/ :id
Scenario ID | API ID | Module | Test Scenario | Test Type | Priority
TS-GET-001 | API-003 | Get Booking | Verify retrieving a booking with a valid ID | Positive | High
TS-GET-002 | API-003 | Get Booking | Verify retrieving different bookings using valid IDs | Functional | Medium
TS-GET-003 | API-003 | Get Booking | Verify API behavior with a non-existing booking ID | Negative | High
TS-GET-004 | API-003 | Get Booking | Verify API behavior with an invalid booking ID format | Negative | Medium
TS-GET-005 | API-003 | Get Booking | Verify booking response contains all expected fields | Functional | High
TS-GET-006 | API-003 | Get Booking | Verify booking dates are returned correctly | Functional | Medium
TS-GET-007 | API-003 | Get Booking | Verify booking response content type | Functional | Medium
API-004— POST/ booking
Scenario ID | API ID | Module | Test Scenario | Test Type | Priority
TS-CREATE-001 | API-004 | Create Booking | Verify creating a booking with valid data | Positive | High
TS-CREATE-002 | API-004 | Create Booking | Verify creating a booking with different valid data | Positive | Medium
TS-CREATE-003 | API-004 | Create Booking | Verify creating a booking with missing firstname | Negative | High
TS-CREATE-004 | API-004 | Create Booking | Verify creating a booking with missing lastname | Negative | High
TS-CREATE-005 | API-004 | Create Booking | Verify creating a booking with missing totalprice | Negative | High
TS-CREATE-006 | API-004 | Create Booking | Verify creating a booking with missing depositpaid | Negative | Medium
TS-CREATE-007 | API-004 | Create Booking | Verify creating a booking with missing bookingdates | Negative | High
TS-CREATE-008 | API-004 | Create Booking | Verify creating a booking with missing additionalneeds | Negative | Low
TS-CREATE-009 | API-004 | Create Booking | Verify creating a booking with invalid totalprice | Negative | High

## Test Case
Test Case ID | Scenario ID | API ID | Test Case | Preconditions | Test Data | Test Steps | Expected Result | Actual Result | Evidence | Status
TC_001 | TS-AUTH-001 | API-001 | Verify authentication with valid credentials | Internet connection available Valid credentials available Tool testing available | Username: admin Password: password123 URL: https://restful-booker.herokuapp.com/auth | 1.Open the tool testing 2.Enter URL 3.Select test method 4.Enter header data 5.Select body items 6. Enter body request 7. Click on ""Send"" button" | The tool testing should be opened The URL should be entered Test method should be selected Header data should be entered Body items should be selected Body request should be entered ""Send"" button should be clicked Status code shoud be displayed 200 ok Body response should be displayed token The users should login successfully with valid credentials. | Tool testing "Postman" screen has been opened. URL "https://restful-booker.herokuapp.com/auth" has been entered. Test method "POST" has been selected. Header data "Key = Content-Type", " Value = application/json" have been entered. Body items "raw" and "JSON" have been selected. Body request { "username" : "admin", "password" : "password123" } has been entered. ""Send"" button has been clicked. Status code "200 ok" has been displayed. Body response "token: 38745c7cfbddeff" has been displayed. Test result has been completed successfully. |  | PASS
TC_002 | TS-AUTH-002 | API-001 | Verify authentication with invalid username | Internet connection available Invalid username available Tool testing available | Username: adminMN Password: password123 URL: https://restful-booker.herokuapp.com/auth | 1.Open the tool testing 2.Enter URL 3.Select test method 4.Enter header data 5.Select body items 6. Enter body request with invalid username 7. Click on "Send" button | The tool testing should be opened The URL should be entered Test method should be selected Header data should be entered Body items should be selected Body request should be entered ""Send"" button should be clicked Status code shoud be displayed Body response should be displayed The users should not login with invalid username | Tool testing "Postman" screen has been opened. URL "https://restful-booker.herokuapp.com/auth" has been entered. Test method "POST" has been selected. Header data "Key = Content-Type", " Value = application/json" have been entered. Body items "raw" and "JSON" have been selected. Body request { "username" : "adminMN", "password" : "password123" } has been entered. "Send" button has been clicked. Status code "200 ok" has been displayed. Body response "reason: Bad credentials" has been displayed. The users cannot login with invalid username. |  | PASS
TC_003 | TS-AUTH-005 | API-001 | Verify authentication with missing password | Internet connection available Valid username available Tool testing available | Username: admin URL: https://restful-booker.herokuapp.com/auth | 1.Open the tool testing 2.Enter URL 3.Select test method 4.Enter header data 5.Select body items 6. Enter body request with valid username and none password 7. Click on "Send" button | The tool testing should be opened The URL should be entered Test method should be selected Header data should be entered Body items should be selected Body request should be entered ""Send"" button should be clicked Status code shoud be displayed Body response should be displayed The users should not login with missing password | Tool testing "Postman" screen has been opened. URL "https://restful-booker.herokuapp.com/auth" has been entered. Test method "POST" has been selected. Header data "Key = Content-Type", " Value = application/json" have been entered. Body items "raw" and "JSON" have been selected. Body request { "username" : "admin", } has been entered. "Send" button has been clicked. Status code "200 ok" has been displayed. Body response "reason: Bad credentials" has been displayed. The users cannot login with missing password. |  | PASS
TC_004 | TS-BOOK-003 | API-002 | Verify retrieving booking IDs by lastname | Internet connection available Test datas available Tool testing available | URL: https://restful-booker.herokuapp.com/booking?lastname=Jones Method: GET | 1.Open the tool testing 2.Enter URL 3.Select test method 4.Select body items 5. Click on "Send" button | The tool testing should be opened The URL should be entered Test method should be selected Body items should be selected "Send" button should be clicked Status code shoud be displayed Body response should be displayed The users should retrieve booking id by last name | Tool testing ""Postman"" screen has been opened. URL "https://restful-booker.herokuapp.com/booking?lastname=Jones" has been entered. Test method "GET" has been selected. Body items "NONE" has been selected. "Send" button has been clicked. Status code ""200 ok"" has been displayed. Body response "bookingid: 1" and "bookingid: 6" have been displayed. The users can retrieve booking ID by lastname |  | PASS
TC_005 | TS-BOOK-002 | API-002 | Verify retrieving booking IDs by firstname | Internet connection available Test datas available Tool testing available | URL: https://restful-booker.herokuapp.com/booking?firstname=Jim Method: GET | 1.Open the tool testing 2.Enter URL 3.Select test method 4.Select body items 5. Click on ""Send"" button | The tool testing should be opened The URL should be entered Test method should be selected Body items should be selected ""Send"" button should be clicked Status code shoud be displayed Body response should be displayed The users should retrieve booking id by first name | Tool testing "Postman" screen has been opened. URL "https://restful-booker.herokuapp.com/booking?firstname=Jim" has been entered. Test method "GET" has been selected. Body items "NONE" has been selected. "Send" button has been clicked. Status code "200 ok" has been displayed. Body response "bookingid: 30","bookingid: 31" and "bookingid: 33" have been displayed. The users can retrieve booking ID by firstname. |  | PASS
TC_006 | TS-CREATE-001 | API-004 | Verify creating a booking with valid data | Internet connection available Test datas available Tool testing available | URL: https://restful-booker.herokuapp.com/booking Method: POST Header: Content-Type: application/json Body request: { "firstname": "Jim", "lastname": "Brown", "totalprice": 111, "depositpaid": true, "bookingdates": { "checkin": "2018-01-01", "checkout": "2019-01-01" }, "additionalneeds": "Breakfast" } | 1.Open the tool testing 2.Enter URL 3.Select test method 4.Enter header data 5.Select body items 6. Enter body request 7. Click on "Send" button | The tool testing should be opened The URL should be entered Test method should be selected Header data should be entered Body items should be selected Body request should be entered "Send" button should be clicked Status code shoud be displayed Body response should be displayed The users should create a booking with valid data. | Tool testing "Postman" screen has been opened. URL "https://restful-booker.herokuapp.com/booking" has been entered. Test method "POST" has been selected. Header data "Key = Content-Type", " Value = application/json" have been entered. Body items "raw" and "JSON" have been selected. Body request has been entered: { "firstname": "Jim", "lastname": "Brown", "totalprice": 111, "depositpaid": true, "bookingdates": { "checkin": "2018-01-01", "checkout": "2019-01-01" }, "additionalneeds": "Breakfast" } "Send" button has been clicked. Status code "200 ok" has been displayed. Body response "bookingid: 2215" has been displayed. The users can create a booking successfully with valid data. |  | PASS

## Test Summary Report
Project Overview
This project focuses on testing the functionality of a web application that provides hotel booking services. API testing was performed to verify the application's backend functionality related to user authentication, booking retrieval, and booking creation. The testing was conducted using Postman to validate API requests and responses, including HTTP status codes, response data, and functional behavior based on the defined requirements and test scenarios.
In Scope
The following functionalities were included in the testing scope: Verify authentication with valid credentials Verify authentication with invalid username Verify authentication with missing password Verify retrieving booking IDs by lastname Verify retrieving booking IDs by firstname Verify creating a booking with valid data
Out of Scope
All other functionalities and features of the hotel booking application that are not explicitly included in the testing scope are out of scope for this project.
Test Environment & Tools
Testing Tool: Postman Application: Hotel Booking Web Application API: Booking-related APIs Data Format: JSON Protocol: HTTP/HTTPS
Test Execution Summary
| Test Result | Number
| Total Test Cases | 30
| Passed | 6
| Failed | 0
| Blocked | 0
| Not Executed | 24
| Pass Rate | 100%
Test Results
Test Case | Test Case ID | Status
Verify authentication with valid credentials | TC_001 | PASS
Verify authentication with invalid username | TC_002 | PASS
Verify authentication with missing password | TC_003 | PASS
Verify retrieving booking IDs by lastname | TC_004 | PASS
Verify retrieving booking IDs by firstname | TC_005 | PASS
Verify creating a booking with valid data | TC_006 | PASS
Defect Summary
No valid defects were identified during the testing activities.
Conclusion
All planned test cases were executed successfully, and the tested functionalities behaved as expected within the defined testing scope.
Recommendation
Based on the test results, the tested functionalities are considered acceptable within the defined scope.